Shettleston Harriers

2014 -2016

Development Plan

Development Area: Athlete Recruitment and Development    Lead person

| Objectives What are we trying to achieve? | Actions How are we going to achieve it? | Personnel Who is going to do it? | Completion date | What will it cost? |
| --- | --- | --- | --- | --- |
| 1. Provide coaching opportunities for all athletes of all abilities | a. Ensure that a clear Coaching Structure is in place for all athletes b. Create links for athletes with a Disability so they can participate and improve in athletics c. Specialist coaches provide from sources out with the club if appropriate where gaps are identified in areas such as jumps and javelin d. Provide coaching training and CPD in identified area of development | a, b,c, Chairperson Coaching, Coaching Co-ordinators, Coaches d. Chairperson Coaching, Coaching Co-ordinators, Coaches, Club Together officer | - 28/2/15 - 30/11/14 - 31/1/15 - 31/1/15 | a and b – no cost c – funds will be made available if appropriate d. – appropriate £3000 per annum * |
| 2. Ensure coaching and competition pathway operates effectively | Clear athlete and coaching pathway available for all members | Lead Coaching Co-ordinator, other coaching coordinators, Team Managers, Club Captains | 28/2/15 | funds will be made available if appropriate |
| 3. Support developing athletes into regional and national level events | Specialist coaches provide dor sources out with the club if appropriate | Chairperson Coaching, Coaching Co-ordinators, Team Mangers, Club Captains, Coaches | 31/1/15 | £600 per annum * |
| 4. Athlete retention | Montoring of athletes progression through career and planning to ensure that retention will increase | Chairperson Coaching, Coaching Co-ordinators, Team Mangers, Club Captains, Coaches | 31/12/16 | funds will be made available if appropriate |

- Further funds will be made available if appropriate

Development Area:  Coach and Officials Development

| Objectives What are we trying to achieve? | Actions How are we going to achieve it? | Personnel Who is going to do it? | Completion date | What will it cost? |
| --- | --- | --- | --- | --- |
| 1. Increase the number of coaches and officials actively involved in the Club | a. Signpost interested coaches and officials to Education Opportunities as identified in personal CPD plans b. Develop a volunteer recruitment plan that will target 16 – 25 year olds, parents and 50 plus to help coach/lead at Club Nights on a rotation c. Identify funding to support coaches and officials to gain qualifications | Lead Coach Co-ordinator , Social/Volunteer Officer, Coaching Committee, Treasurer, Club Together Officer | 30/6/15 | £3000 * |
| 2. Support coaches and officials in the Club to develop their experience and knowledge | a. Signpost coaches/officials to education opportunities locally, regionally and nationally, with a minium of 20% of club coaches/officials attneding b. Introduce an structured mentoring programme where experienced coaches can support newer coaches, also allow them to rotate around events c. Identify funding to support coaches and officials to access further education as identified in the coach/official’s development plan | Lead Coach Co-ordinator Social/Volunteer Officer, Club Together Officer, Coaching Committee | 31/12/16 | N/A |
| 3. Enhance the coaching structure in the Club (see athlete recruitment and development above) | a. Continue the regular coaching meetings- organise GAA and SA mentors and in-house CPD at least twice per year b. Place the Clubs coaching structure on our website (with contacts) c. Ensure the Club has job descriptions for all coaching roles | Lead Coaching Co-ordinator, Coaching Chairperson, Coaching sub groups – sprints/hurdles, Jumps, Throws, Endurance, Off Road | 31/12/14 | N/A |

- Further funds will be made available if appropriate

Development Area:  Volunteer Recruitment and Development

| Objectives What are we trying to achieve? | Actions How are we going to achieve it? | Personnel Who is going to do it? | Completion date | What will it cost? |
| --- | --- | --- | --- | --- |
| 1. Provide outline role description so volunteers understand their role | a. Decide on roles that require to be fulfilled by Club b. Outline roles (find templates from other organisations) c. Communicate this with members | President, Social/Volunteer Officer Club Together Officer | 31/3/15 | N/A |
| 2. Create a system for recruiting, retaining and recognising volunteers | a. Recruit volunteers through parents evening (see below) and at other club events/activities b. Each year, at Annual Club Awards evening, have awards for club members and volunteers. | Social/Volunteer Officer Club Together Officer | 30/11/14 | a. £180 per annum * b. £250 per annum * |
| 3. Provide Regular Parents Evenings | Every new young member, with parent, should attend a parent’s evening, with parents night at least 2 times a year | Social/Volunteer Officer Chairperson coaching, Club Together officer | 31/1/15 | £180 per annum * |

- Further funds will be made available if appropriate

Development Area:  Training and Competition

| Objectives What are we trying to achieve? | Actions How are we going to achieve it? | Personnel Who is going to do it? | Completion date | What will it cost? |
| --- | --- | --- | --- | --- |
| 1. Provide competition at all Levels | a. Ensure we have Team Managers for each competition b. Ensure coaches, parents, athletes are aware of competition pathway and how each competition operates – use website, social media, email and letters c. Ensure we have coaches in place to support the preparation for these matches (links to Coaches Meetings , see above) | Lead Team Manager, Lead Club Captain, Lead Coaching Coordinator, Coaching Committee, Communication Officer | 31/3/15 | N/A |
| 2. Create a fixture list appropriate for our Club Athletes | Signpost members especially new and young members to competition opportunities locally, regionally and nationally – website, social media, email, letters | Lead Team Manager, Lead Club Captain, Lead Coaching Coordinator, Coaching Committee, Communication Officer | 31/3/15 | N/A |
| 3. Organise an event/s | a. Open Graded Track&Field Meetings b. Allan Scally Road Relay c. Club Events – Track /Field, Christmas Handicap d. Junior ParkRun/Local Junior Run | Event Officer/Assist Secry Sub Committee for appropriate event | a to c annual ongoing d. 31/1/15 | a to c £2400 appropriate d. not known |

Development Area:  Partners (Develop School to Club Links)

| Objectives What are we trying to achieve? | Actions How are we going to achieve it? | Personnel Who is going to do it? | Completion date | What will it cost? |
| --- | --- | --- | --- | --- |
| 1. Link Club officially to Run, Jump and Throw Clubs and jogscotland groups where appropriate | a. Create clear pathway for members of Run, jump and Throw Clubs to the Club b. Put in place membership options for membership of Run, Jump and Throw Clubs and jogscotland to become club members | - Coaches at RJT, Coaching Coordinators b. Membership Officer | 31/12/14 | Self Funding N/A |
| 2. Introduce formal Come and Try Days following key local school events | Invite pupils from key events a)Sportshall b) XC and c) Track and Field to organised coaching sessions and ensure this is part of the club’s ongoing work. A miniumum of 10 people per event | Lead Coaching Coordinator, coaches Club Together Officer | 31/12/16 | £6000 approp * |
| 3. Work in partnership with key agencies | a. Regularly attend and participate in Local Athletics Partnership with Glasgow Sport, ScottishAthletics, GAA, Active Schools and other local and national partners b. Link with Sports Development Team in Glasgow Life and Regional Manager for ScottishAthletics to help with Development Plan | Vice President Club Together Officer Committee | a. 31/12/16 b. 31/10/14 | N/A |

- Further funds will be made available if appropriate

Development Area: Management (Administration, Welfare, Finance, Facilities/Equipment, Marketing)

| Objectives What are we trying to achieve? | Actions How are we going to achieve it? | Personnel Who is going to do it? | Completion date | What will it cost? |
| --- | --- | --- | --- | --- |
| 1. Improve the effectiveness of the Club Management Structure | a. Use this Development Plan as key driver for Club Management and Development b. Review the structure of the Club and identify any key gaps or change required c. Organise annual seminar/planning day for the Club to ensure full club support | President and Club Committee | a and b 3/12/16 c 31/3/15 | N/A |
| 2. Maintain and Develop facilities for Clubs | a. Sub Group formed to work with Local Authority to develop and maintain facilities for athletics in the area b. Work with Local Authority to ensure Club’s access to the facility on appropriate evenings | Vice President, other office bearers and Club Together Officer | 31/1/14 | N/A |
| 3. Ensure robust Welfare/Child Protection procedures are in place | a. Ensure Club Welfare Officer has attended suitable training – ‘In Safe Hands’ b. Ensure all Club Coaches and volunteers working with Children have attended a Child Protection Course c. Ensure the Club Welfare Policy, procedures and contacts are on the website and in our Club Information booklet d. Ensure all members who are undertaking regulated work have relevant Disclosure Scotland Checks in place and Welfare Officer maintains database | Club Welfare Officer with support from Club Committee | 31/12/16 | N/A |
| 4. Develop Club Financial procedures and structures so we can fulfil our Development Plan | a. Identify grants and sponsorship opportunities b. Work with key partners including Glasgow Life, ScottishAthletics, GAA and other local and national partners to tap into any relevant funding that is available c. Support athletes who are at National/International Level – establish criteria and funding model | Treasurer and committee members Club Together Officer | 31/12/16 | N/A |
| 5. Create marketing materials and opportunities for the Club. | a. Produce promotional material for Schools (see partnership working) b. Maintain club website and social media presence c. Develop the Club webpage by adding further sections and recruiting key volunteers to maintain and regularly update the site d. Produce parent/guardian/member welcome pack with all key club details | Communication Officer Club Together Officer | a, b and c 31/12/16 d 31/3/15 (updated) | £150 per annum * |

- Further funds will be made available if appropriate